## Tabelle1
Risk Name | Risk Description | Risk Probability of Occurence | Risk Impact | Risk Factor | Risk Migration | Person in Charge of Tracking
Time Managment | Team has problems managing their time contrains. (e.g. Tasks are to time intense other tasks hardly use any time) | 70% | 4 | 2.8 | Cancel feature and restructe priorization in sprint | Daniel
Random Songs | Team starts singing random songs in meetings | 50% | 5 | 2.5 | Ignore singing and bring actual topics into conversations | Andreas
Missing Sprite | Developer need a specific sprite to bring their scene to life, which is not in the library of the team. | 80% | 3 | 2.4 | Search for fitting sprite (e.g. Fivver service) | Lawand
Technical Limitations | Team has an idea which can’t be implemented with LitiEngine | 20% | 5 | 1 | Cancel feature and compensate with similar possible feature. | Daniel
PC-Trouble | Individual Computer of a developer has problems | 10% | 8 | 0.8 | Change to back up system | Leon
Github down | Github is not working anymore and there is no way to commit to the repository. | 1% | 10 | 0.1 | Self host Git instance on own server | Andreas