## issues
Issue Id | Summary | Created | Resolved | Type | Spent Time | Status | Estimation | RUP Workflow | RUP Phase | Description | Ucs | Ucs2
LIT-21 | 3rd Week Blog entry | 2020-10-15 13:34 | 2020-10-19 21:42 | Task | 60 | Done | 60 | Project Management | No rup phase |  | -
LIT-22 | 2 Peer Reviews | 2020-10-15 13:34 | 2020-10-19 21:41 | Task |  | Done | 60 | Project Management | No rup phase |  | -
LIT-24 | 4th Week Blog Entry | 2020-10-15 13:34 | 2020-10-27 08:40 | Task | 60 | Done | 60 | Project Management | No rup phase |  | -
LIT-25 | Complete Homework for this Week | 2020-10-15 13:35 | 2020-10-19 21:41 | Task | 120 | Done | 180 | Project Management | No rup phase | [x] Fill out SRS template in Markup [x] Version control it in your git [x] Keep documentation clearly seperated from code [x] Look at examples from past blogs [x] Create the Overall Use case Diagramm: draw.io [x] Submit both as a peer reviewed task by end of this week (SRS Template Markup & Use Case Diagramm) | -
LIT-27 | Multiplayer | 2020-10-18 21:01 | 2020-11-04 22:44 | Epic | 621 | Done | 1140 | No rup workflow | No rup phase |  | -
LIT-28 | Textchat über direkte IP Verbindung auf Konsolen Niveau | 2020-10-18 21:02 | 2020-11-04 22:35 | No Type | 60 | Done | 300 | No rup workflow | No rup phase |  | -
LIT-29 | Verbindung auf einen Server, der die Kommunikation regelt | 2020-10-18 21:02 | 2020-11-04 22:35 | No Type | 68 | Done | 480 | No rup workflow | No rup phase |  | -
LIT-30 | Komplexere Informationen schicken | 2020-10-18 21:03 | 2020-11-04 22:35 | No Type |  | Done |  | No rup workflow | No rup phase |  | -
LIT-31 | Optimierung der Latenz | 2020-10-18 21:03 | 2020-11-04 22:35 | No Type |  | Done |  | No rup workflow | No rup phase |  | -
LIT-32 | Repos auf JAVA umziehen | 2020-10-18 21:05 | 2020-10-18 21:31 | No Type | 90 | Done | 60 | Configuration & Change Management | No rup phase |  | -
LIT-33 | Create Communication Protocol | 2020-10-20 11:27 | 2020-11-04 22:35 | No Type |  | Done | 180 | No rup workflow | No rup phase |  | -
LIT-34 | Homework Week 4 | 2020-10-24 21:01 | 2020-10-27 10:40 | Task |  | Done | 180 | Project Management | No rup phase | [x] Define Scope of your project to 5 use cases [x] Download Use Case Template [x] Version Control it and embed it in git [x] Fill Out 2 UC (activity diagram, screenshot, narration) -> Concentrate on the Activity diagram -> Wireframing Screenshots -> Next week: Cucumber for narration (you can start now) -> End of semester 5 UC due for scope (you define it and let me know) | -
LIT-35 | Setup cucumber | 2020-10-27 10:28 | 2020-11-03 09:57 | No Type | 120 | Done | 120 | Configuration & Change Management | No rup phase |  | -
LIT-46 | Testing and evaluating UI Implementation | 2020-10-27 10:43 | 2020-10-30 11:49 | No Type | 261 | Done | 480 | Analysis & Design | No rup phase |  | -
LIT-47 | UI for Chat | 2020-10-27 10:47 | 2020-11-03 01:18 | No Type | 493 | Done | 180 | Implementation | No rup phase |  | -
LIT-51 | UC -- Attack | 2020-11-03 12:33 | 2020-11-07 00:04 | Story |  | Done |  | Analysis & Design | Construction |  | -
LIT-52 | Use Cases | 2020-11-03 12:34 | 2020-11-10 13:12 | Epic | 533 | Done | 660 | Project Management | Elaboration |  | -
LIT-53 | UC -- Catching | 2020-11-03 12:35 | 2020-11-07 00:15 | Story |  | Done |  | Analysis & Design | Construction |  | -
LIT-62 | 6th Week Blog Post | 2020-11-05 20:54 | 2020-11-06 19:19 | Task | 120 | Done |  | Project Management | Elaboration | - Cucumber autocomplete - .feature files (also in UCS) - YouTrack (RUP-Phases) - Sprint cancel -> new Sprint - New plan (UCDD) (+) - Already implemented UCs (+) - Screenshot YouTrack IDE task list - Git Branchin in IDE with from YT tasks - Example time tracking - Screenshots YouTrack AgileBoard (perhaps even Burndown Chart and Cummulative Flow) - Screenshot of UC-Tast with dependencies | -
LIT-63 | Test UCs with cucumber | 2020-11-05 20:56 | 2020-11-08 23:22 | Task | 270 | Done | 180 | Test | Construction | Get a correct method call working with Cucumber | -
LIT-79 | Refactoring UI | 2020-11-10 13:10 | 2020-11-13 22:10 | Task | 247 | Done | 240 | Implementation | Construction |  | -
LIT-80 | Refactoring CE | 2020-11-10 13:10 | 2021-01-09 16:07 | Task | 1478 | Done | 240 | Implementation | Transition |  | -
LIT-81 | Refactoring Liti | 2020-11-10 13:11 | 2020-11-19 18:56 | No Type | 139 | Done | 240 | Implementation | Transition |  | -
LIT-82 | Diagramms and Architecture for Refactoring | 2020-11-10 13:12 | 2020-11-13 22:12 | Task | 480 | Done | 180 | Analysis & Design | Elaboration |  | -
LIT-83 | Blog Post Week 7 | 2020-11-10 21:16 | 2020-11-10 22:09 | Task | 30 | Done | 60 | Project Management | Elaboration |  | -
LIT-86 | Save Game | 2021-04-09 23:04 |  | Todo |  | ToDo | 120 | Analysis & Design | Inception | Create Datastructure for Savegame Files: - Gamestate - Position - Inventory - Character Stats (lvl) - Team with Stats - Skills - etc. | -
LIT-88 | Implement Pseudo Random Function | 2021-04-09 23:07 |  | Todo |  | ToDo | 60 | Implementation | Construction | - implement the pseudo random algrothm from LoL to our CE | -
LIT-101 | SRS | 2021-04-09 23:29 | 2021-04-22 23:58 | Todo | 180 | Done | 60 | Project Management | Elaboration | update SRS | -
LIT-102 | RUP | 2021-04-09 23:30 |  | Todo |  | ToDo | 60 | Project Management | Elaboration | update | -
LIT-103 | SAD | 2021-04-09 23:30 | 2021-04-22 23:58 | Todo | 60 | Done | 60 | Project Management | Elaboration | update | -
LIT-104 | Document Peerreviews | 2021-04-09 23:31 | 2021-04-11 09:57 | No Type | 60 | Done | 60 | Project Management | Elaboration |  | -
LIT-105 | Document Peerreviews | 2021-04-09 23:32 | 2021-04-11 09:57 | No Type | 60 | Done | 60 | Project Management | Elaboration |  | -
LIT-106 | Create Sprint | 2021-04-09 23:33 | 2021-04-11 09:57 | No Type | 30 | Done | 30 | Project Management | Construction |  | -
LIT-107 | Setup Meeting tool | 2021-04-10 23:48 | 2021-04-10 23:49 | Task | 30 | Done | 30 | Project Management | Construction |  | -
LIT-108 | Blog Entry and Peer Reviews | 2021-04-12 16:32 | 2021-04-12 16:32 | No Type | 270 | Done | 360 | Project Management | Elaboration |  | -
LIT-110 | Welcomeback Blog | 2021-04-20 02:17 | 2021-04-20 02:17 | No Type | 60 | Done | 90 | Project Management | Elaboration |  | -
LIT-112 | Cat fighting | 2021-04-22 21:49 |  | Task |  | In Progress | 240 | Implementation | Construction |  | -
LIT-114 | Rip Threads out of CE | 2021-04-23 14:02 |  | No Type |  | ToDo | 300 | Implementation | Construction | Rip Threads out of our CE in order to resolve threading synchronisation problems | -
LIT-9 | Character Structure | 2020-10-15 13:32 | 2020-10-27 10:04 | Story | 120 | Done | 300 | Analysis & Design | No rup phase |  | Battle
LIT-11 | littleBeasts | 2020-10-15 13:32 | 2020-10-20 11:24 | Task | 60 | Done | 60 | Analysis & Design | No rup phase |  | Battle
LIT-13 | Battles Structure | 2020-10-15 13:33 | 2020-10-27 10:14 | Story | 360 | Done | 480 | Analysis & Design | No rup phase |  | Battle
LIT-14 | Damage | 2020-10-15 13:33 | 2020-10-27 10:05 | Task | 30 | Done | 60 | Analysis & Design | No rup phase | Basic Calculations Random number generator Damage Range Crits Modifier | Battle
LIT-36 | Calculation Engine | 2020-10-27 10:29 |  | Epic | 2734 | ToDo | 2520 | No rup workflow | No rup phase |  | Battle | Looting
LIT-37 | UI | 2020-10-27 10:29 |  | Epic | 2499 | ToDo | 2940 | No rup workflow | No rup phase |  | Battle | In Game Menu
LIT-38 | Implement Damage Class | 2020-10-27 10:30 | 2020-11-02 20:05 | No Type | 121 | Done | 180 | Implementation | No rup phase |  | Battle
LIT-42 | Implement AI | 2020-10-27 10:32 | 2020-11-06 22:02 | No Type | 109 | Done | 120 | Implementation | No rup phase |  | Battle
LIT-44 | Implement Entities | 2020-10-27 10:40 | 2020-10-30 17:52 | No Type | 174 | Done | 180 | Implementation | No rup phase | Entity is a class which has all the stats of a entitiy. This should include, but is not limited to: https://github.com/LittleBeasts/documentation/tree/master/datastructure/character | Battle
LIT-54 | Battle Overlay | 2020-11-04 22:42 | 2020-11-06 01:41 | No Type | 311 | Done | 180 | Implementation | Construction |  | Battle
LIT-57 | Implement Battle | 2020-11-04 22:49 | 2020-12-07 03:02 | No Type | 210 | Done | 180 | Implementation | Construction | Implement Battle Mechanics like: Turn order: - Speed determines who has a turn. Deal Damage to Entity Entity Status End of Battle | Battle
LIT-58 | Battle Trigger | 2020-11-04 22:50 | 2020-11-07 00:03 | No Type | 206 | Done | 240 | Implementation | Construction | Monster Spawn Enter Battle Whenever 'B' is pressed (Open attack menu) | Battle
LIT-59 | Choose AI Monster Attack | 2020-11-04 22:52 | 2020-11-06 22:05 | Story | 60 | Done | 120 | Test | Construction |  | Battle
LIT-89 | Draw Pet | 2021-04-09 23:09 | 2021-04-11 09:56 | Todo | 90 | Done | 120 | Implementation | Construction | - create routine which also displays pet of character: - implement sprites to litidata - position correctly in battle stance - use attack animation for attacking | Battle | Environmental Interactions
LIT-18 | Catching | 2020-10-15 13:33 | 2020-10-27 10:19 | Task | 60 | Done | 60 | Analysis & Design | No rup phase |  | Catch & Collect
LIT-40 | Implement catching | 2020-10-27 10:30 | 2020-11-02 20:05 | No Type | 48 | Done | 180 | Implementation | No rup phase |  | Catch & Collect
LIT-61 | Catching | 2020-11-04 22:56 | 2020-11-06 23:35 | No Type | 83 | Done | 240 | Test | Construction | Attack Catching has to be defined Entity Type Player has to be defined Attack Catching is a Standard attack for an entity of type Player Catching will be called | Catch & Collect
LIT-78 | Catching UI | 2020-11-10 13:05 |  | Task |  | In Progress | 180 | Implementation | Construction |  | Catch & Collect
LIT-10 | Protagonist | 2020-10-15 13:32 | 2020-10-20 11:24 | Task | 60 | Done | 120 | Analysis & Design | No rup phase |  | Environmental Interactions
LIT-20 | Story Progress | 2020-10-15 13:33 | 2020-10-27 10:09 | Task | 60 | Done | 120 | Analysis & Design | No rup phase | Story Progress Save Game Architecture | Environmental Interactions
LIT-91 | Map Concepts | 2021-04-09 23:13 | 2021-04-11 09:57 | Todo | 90 | Done | 60 | Analysis & Design | Inception |  | Environmental Interactions | Screenchange
LIT-94 | Map Sketches | 2021-04-09 23:17 | 2021-04-21 23:07 | Todo |  | Done | 660 | Analysis & Design | Inception | - Arkham: - Flea Market 2h ("Schwarzmarkt" kleine Stände, relativ viel NPCs) Daniel Lois--> rest BS-NPCs - Arkham City 2h ( man könnte viel absperren) Andreas - Industrial Zone 1h (Lagerhäuser - Hafen outskirts - Hobos) - Residential Zone 1h (Ladengeschäfte) Mr.Paulsen - New Campus 2h (2-3 NPCs mit Büros + Courtyard) Leon Prof Weintraub - Park (with church) 1h Stinky Pete (HOBO) - Crater (destroyed campus) 2h Lawand Agent Scully - Catacombs (plot twist, monster usw.) | Environmental Interactions | Screenchange
LIT-95 | Map Sketches Arkham | 2021-04-09 23:18 | 2021-04-21 23:07 | Todo | 120 | Done | 120 | Analysis & Design | Inception | - Industrial Zone 1h (Lagerhäuser - Hafen outskirts - Hobos) - Residential Zone 1h (Ladengeschäfte) Mr.Paulsen | Environmental Interactions | Screenchange
LIT-96 | Flea Market | 2021-04-09 23:20 | 2021-04-13 03:31 | Todo | 105 | Done | 180 | Analysis & Design | Inception | ("Schwarzmarkt" kleine Stände, relativ viel NPCs) Daniel Lois--> rest BS-NPCs | Environmental Interactions | Screenchange
LIT-97 | New Campus | 2021-04-09 23:22 | 2021-04-16 21:29 | Todo | 190 | Done | 180 | Analysis & Design | Inception | - New Campus 2h (2-3 NPCs mit Büros + Courtyard) Leon Prof Weintraub - Park (with church) 1h Stinky Pete (HOBO) | Environmental Interactions | Screenchange
LIT-98 | Crater | 2021-04-09 23:23 | 2021-04-20 13:36 | Todo | 130 | Done | 180 | Analysis & Design | Inception | - Crater (destroyed campus) 2h Lawand Agent Scully - Catacombs (plot twist, monster usw.) | Environmental Interactions | Screenchange
LIT-99 | Pet logic | 2021-04-09 23:26 | 2021-04-11 09:56 | Todo | 240 | Done | 240 | Implementation | Construction | - create follow routine for pet - implement pet in team | Environmental Interactions
LIT-100 | Story outline | 2021-04-09 23:28 | 2021-04-11 09:57 | Todo | 160 | Done | 120 | Analysis & Design | Inception | create rough plot for the Arkham Story Ark. ( should last around 30-60 Minutes of Gameplay) | Environmental Interactions | Dialog
LIT-113 | Add maps to Game | 2021-04-22 21:50 |  | Task | 720 | Ready for Review | 720 | Implementation | Construction |  | Environmental Interactions
LIT-16 | Attacks | 2020-10-15 13:33 | 2020-10-20 11:24 | Task | 60 | Done | 120 | Analysis & Design | No rup phase |  | Fight
LIT-43 | Implement Attacks | 2020-10-27 10:37 | 2020-10-31 12:02 | No Type | 127 | Done | 180 | Implementation | No rup phase |  | Fight
LIT-55 | Choose Attacks Overlay | 2020-11-04 22:42 | 2020-11-06 23:05 | No Type | 389 | Done | 360 | Implementation | Construction |  | Fight
LIT-56 | Connect CEEntity with LitiEntitys | 2020-11-04 22:45 | 2020-11-06 22:03 | No Type | 90 | Done | 60 | Implementation | Construction |  | Fight
LIT-60 | Choose Player Attack | 2020-11-04 22:54 | 2020-11-07 00:04 | No Type | 120 | Done | 120 | Test | Construction |  | Fight
LIT-111 | Whatever kay wants about estimation | 2021-04-22 21:44 |  | Usability Problem |  | ToDo | 180 | Project Management | Construction |  | FU
LIT-15 | Loot | 2020-10-15 13:33 | 2020-10-27 10:07 | Task | 90 | Done | 60 | Analysis & Design | No rup phase | Loottable: Gegenstände, Warscheinlichkeit, Bedingungen: JSON Items | Looting
LIT-41 | Implement Looting | 2020-10-27 10:31 | 2020-10-31 15:03 | No Type | 267 | Done | 240 | Implementation | No rup phase |  | Looting
LIT-73 | Item Class | 2020-11-10 12:41 | 2021-04-19 20:48 | Task | 50 | Done | 120 | Analysis & Design | Elaboration |  | Looting
LIT-74 | Inventory | 2020-11-10 12:41 |  | Task | 160 | Ready for Review | 240 | Implementation | Construction |  | Looting
LIT-75 | Item Structure | 2020-11-10 12:42 | 2020-11-10 22:13 | Task | 35 | Done | 60 | Analysis & Design | Elaboration |  | Looting
LIT-76 | Inventory Structure | 2020-11-10 12:42 | 2020-11-10 22:16 | Task | 30 | Done | 60 | Analysis & Design | Construction |  | Looting
LIT-77 | Inventory UI | 2020-11-10 13:05 | 2021-04-09 14:56 | Task | 275 | Done | 180 | Implementation | Construction |  | Looting
LIT-90 | Itemlist | 2021-04-09 23:11 |  | Todo |  | ToDo | 120 | Analysis & Design | Inception | brainstorm for itemlist: - weapons - armor - usables - story items | Looting | Battle
LIT-109 | Implement Item Class | 2021-04-19 20:50 | 2021-04-21 11:27 | Task | 160 | Done | 240 | Implementation | Construction |  | Looting
LIT-7 | Movement | 2020-10-15 13:27 | 2020-10-27 10:18 | Task | 60 | Done | 60 | Analysis & Design | No rup phase | * Wie schnell * Welche richtung * Wie bewegt er sich (Karte, Char, Hybrid) * Animation placeholder * Enthält komplettes Movement des Spiels | Movement
LIT-12 | NPCs | 2020-10-15 13:32 | 2020-10-20 11:24 | Task | 60 | Done | 120 | Analysis & Design | No rup phase |  | NPC Interaction
LIT-19 | Dialog Tree | 2020-10-15 13:33 | 2020-10-27 10:16 | Task | 60 | Done | 60 | Analysis & Design | No rup phase | Dialog Options Inherit Structure JSON Statestorage | NPC Interaction | Dialog
LIT-84 | Game Content | 2021-04-09 23:00 |  | Epic | 1035 | ToDo | 1200 | Implementation | Inception | Create the actual content of the game | NPC Interaction | Screenchange
LIT-85 | Dialog Tree | 2021-04-09 23:03 | 2021-04-11 21:06 | Todo | 90 | Done | 120 | Analysis & Design | Inception | Conceptualize a Dialog Tree model for handling the scenes. - should be JSON - should be easy to create/undestand | NPC Interaction | Dialog
LIT-87 | Gamestate | 2021-04-09 23:06 | 2021-04-11 21:06 | Todo | 90 | Done | 120 | Analysis & Design | Inception | Create a structure for holding the gamestate: - paused/menu/battle etc. - story progress - interactions with NPCs - etc. | NPC Interaction | Battle
LIT-5 | Tiles | 2020-10-15 13:26 | 2020-10-27 10:19 | Task | 120 | Done | 60 | Analysis & Design | No rup phase |  | Screenchange
LIT-6 | Map datastructures | 2020-10-15 13:26 | 2020-10-27 10:19 | Story | 360 | Done | 300 | Analysis & Design | No rup phase |  | Screenchange
LIT-8 | Effect Overlay | 2020-10-15 13:28 | 2020-10-27 10:17 | Task | 60 | Done | 180 | Analysis & Design | No rup phase | Dinge die über der Karte liegen Dinge dir über der Karte animiert / generiert werden Konzept schaffen: Was soll es können Was kann es empfangen Wie stellen wir uns das vor? Effekt Klasse definieren Effekt Overlay = Interface | Screenchange
LIT-17 | Taming | 2020-10-15 13:33 | 2020-10-27 10:14 | Task | 60 | Done | 180 | Analysis & Design | No rup phase | Taming System: max tame value, tame calculations littleBeast natures Progress Dialog options | Taming
LIT-39 | Implement taming | 2020-10-27 10:30 | 2020-11-04 22:35 | No Type |  | Done | 300 | Implementation | No rup phase |  | Taming
LIT-2 | Datastructure | 2020-10-15 13:10 |  | Epic | 1615 | No status | 2280 | No rup workflow | No rup phase
LIT-4 | Documentation Backlog | 2020-10-15 13:24 |  | Epic | 1680 | No status | 1830 | No rup workflow | No rup phase
[11 empty] | 3801 | Looting
[11 empty] | 1965 | Environmental Interactions
[11 empty] | 310 | Dialog
[11 empty] | 2210 | Screenchange
[11 empty] | 7174 | Battle
[11 empty] | 1335 | NPC Interaction
[11 empty] | 191 | Catch & Collect
[11 empty] | 786 | Fight
[11 empty] | 60 | Taming
[11 empty] | 2499 | In Game Menu
[11 empty] | 60 | Movement